## Gantt Chart
GANTT CHART - CS401 Software Eng.
PROJECT TITLE |  | Video Game Rental Service |  |  |  |  | COMPANY NAME | [6 empty] | VGRentalZ
PROJECT MEMBERS |  | Ivan Peric / Alvin Derek Tiletile / Yew Loon Mun |  |  |  |  | DATE | [6 empty] | 2020-01-21
WBS NUMBER | TASK TITLE |  | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [9 empty] | PHASE TWO | [9 empty] | PHASE THREE | [9 empty] | PHASE FOUR | [9 empty] | PHASE FIVE | [9 empty] | PHASE SIX | [9 empty] | PHASE SEVEN
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Select Team Members |  | 2020-01-21 | 2020-02-04 | 13 | 100% | bar: WEEK 1 M to WEEK 2 F
1.2 | Select Project |  | 2020-01-21 | 2020-02-04 | 13 | 100% | bar: WEEK 1 M to WEEK 2 F
1.3 | Create Project Docs |  | 2020-01-21 | 2020-02-04 | 13 | 100% | bar: WEEK 1 M to WEEK 2 F
1.4 | Create Repo |  | 2020-01-21 | 2020-02-04 | 13 | 100% | bar: WEEK 1 M to WEEK 2 F
1.5 | High Level Abstract |  | 2020-01-21 | 2020-02-04 | 13 | 100% | bar: WEEK 1 M to WEEK 2 F
2 | Project Definition and Planning
2.1 | UML Project Design |  | 2020-02-07 | 2020-02-21 | 14 | 75% | bar: WEEK 2 M to WEEK 3 F
2.1.2 | UML Finalization |  | 2020-02-12 | 2020-02-21 | 9 | 75% | bar: WEEK 2 M to WEEK 3 F
2.2 | Project Requirements Doc |  | 2020-02-07 | 2020-02-21 | 14 | 75% | bar: WEEK 2 M to WEEK 3 F
2.3 | Gantt Chart |  | 2020-02-07 | 2020-02-21 | 14 | 75% | bar: WEEK 2 M to WEEK 3 F
2.4 | Roles & Responsibilities Doc |  | 2020-02-07 | 2020-02-21 | 14 | 90% | bar: WEEK 2 M to WEEK 3 F
3 | Project Conception and Initiation
3.1 |  |  |  |  | 0 | 0%
3.2 |  |  |  |  | 0 | 0%
3.3 |  |  |  |  | 0 | 0%
3.4 |  |  |  |  | 0 | 0%
3.5 |  |  |  |  | 0 | 0%
3.6 |  |  |  |  | 0 | 0%
4 | Project Performance / Monitoring
4.1 |  |  |  |  | 0 | 0%
4.2 |  |  |  |  | 0 | 0%
4.3 |  |  |  |  | 0 | 0%
4.4 |  |  |  |  | 0 | 0%