## Gantt Chart
GANTT CHART - CS401 Software Eng.
PROJECT TITLE |  | Video Game Rental Service |  |  |  |  | COMPANY NAME | [6 empty] | VGRentalZ
PROJECT MEMBERS |  | Ivan Peric / Alvin Derek Tiletile / Yew Loon Mun |  |  |  |  | DATE | [6 empty] | 2020-01-21
WBS NUMBER | TASK TITLE |  | START DATE | DUE DATE | DURATION | TASK COMPLETE? (Y/N) | PHASE ONE | [9 empty] | PHASE TWO | [9 empty] | PHASE THREE | [9 empty] | PHASE FOUR | [9 empty] | PHASE FIVE | [9 empty] | PHASE SIX | [9 empty] | PHASE SEVEN
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Select Team Members |  | 2020-01-21 | 2020-02-04 | 13 | Y | bar: WEEK 1 M to WEEK 2 F; WEEK 4 M to WEEK 4 T
1.2 | Select Project |  | 2020-01-21 | 2020-02-04 | 13 | Y | bar: WEEK 1 M to WEEK 2 F; WEEK 4 M to WEEK 4 T
1.3 | Create Project Docs |  | 2020-01-21 | 2020-02-04 | 13 | Y | bar: WEEK 1 M to WEEK 2 F; WEEK 4 M to WEEK 4 T
1.4 | Create Repo |  | 2020-01-21 | 2020-02-04 | 13 | Y | bar: WEEK 1 M to WEEK 2 F; WEEK 4 M to WEEK 4 T
1.5 | High Level Abstract |  | 2020-01-21 | 2020-02-04 | 13 | Y | bar: WEEK 1 M to WEEK 2 F; WEEK 4 M to WEEK 4 T
2 | Project Definition and Planning
2.1 | UML Project Design |  | 2020-02-07 | 2020-02-21 | 14 | Y | bar: WEEK 2 M to WEEK 4 T
2.1.2 | UML Finalization |  | 2020-02-12 | 2020-02-21 | 9 | N | bar: WEEK 2 M to WEEK 4 T
2.2 | Project Requirements Doc |  | 2020-02-07 | 2020-02-21 | 14 | Y | bar: WEEK 2 M to WEEK 4 T
2.3 | Gantt Chart |  | 2020-02-07 | 2020-02-21 | 14 | Y | bar: WEEK 2 M to WEEK 4 T
2.4 | Roles & Responsibilities Doc |  | 2020-02-07 | 2020-02-21 | 14 | Y | bar: WEEK 2 M to WEEK 4 T
3 | Project Instantiation
3.1 | Create classes; instantiate objects |  | 2020-02-21 | 2020-03-03 | 12 | x | bar: WEEK 4 M to WEEK 4 T
3.2 | Instantiate appropriate functions |  | 2020-02-21 | 2020-03-03 | 12 | x | bar: WEEK 4 M to WEEK 4 T
3.3 | Instantiate Database |  | 2020-02-21 | 2020-03-03 | 12 | x | bar: WEEK 4 M to WEEK 4 T
3.4 | Simulate objects + data(inventory; customers) |  | 2020-02-21 | 2020-03-03 | 12 | x | bar: WEEK 4 M to WEEK 4 T
4 | Project Instantiation (Part 2)
4.1 | Basic operational webpage |  | 2020-03-03 | 2020-03-17 | 14 | x | bar: WEEK 4 M to WEEK 4 T
4.1.2 | Webpage - Browse inventory |  | 2020-03-03 | 2020-03-17 | 14 | x | bar: WEEK 4 M to WEEK 4 T
4.1.3 | Webpage - Make Purchase |  | 2020-03-03 | 2020-03-17 | 14 | x | bar: WEEK 4 M to WEEK 4 T
4.1.4 | Webpage - Premium |  | 2020-03-03 | 2020-03-17 | 14 | x | bar: WEEK 4 M to WEEK 4 T
4.2 | TBD |  | TBD | TBD | #VALUE! | x | bar: WEEK 4 M to WEEK 4 T
4.3 | TBD |  | TBD | TBD | #VALUE! | x | bar: WEEK 4 M to WEEK 4 T
4.4 | TBD |  | TBD | TBD | #VALUE! | x | bar: WEEK 4 M to WEEK 4 T
5 | Project Instantiation (Part 3)
5.1 | Functional Networking btwn office / warehouse / clients |  | TBD | TBD | #VALUE! | x | bar: WEEK 4 M to WEEK 4 T
5.1.2 | Testing the network |  | TBD | TBD | #VALUE! | x | bar: WEEK 4 M to WEEK 4 T
5.3 | TBD |  | TBD | TBD | #VALUE! | x | bar: WEEK 4 M to WEEK 4 T
5.4 | TBD |  | TBD | TBD | #VALUE! | x | bar: WEEK 4 M to WEEK 4 T
6 | Project Performance + Monitoring
6.1 | Go live with simulated data |  | TBD | TBD | #VALUE! | x | bar: WEEK 4 M to WEEK 4 T
6.2 | Ensure database/website is fully operational |  | TBD | TBD | #VALUE! | x | bar: WEEK 4 M to WEEK 4 T
6.3 | Testing for errors |  | TBD | TBD | #VALUE! | x | bar: WEEK 4 M to WEEK 4 T
6.4 | TBD |  | TBD | TBD | #VALUE! | x | bar: WEEK 4 M to WEEK 4 T